## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
| QA Team | 2025-10-25 | Flight search page returns "No flights found" even for valid routes | Sprint 2 | Backend Team 2 | Logical | Fixed API query issue fetching routes | 2025-10-26 | Closed | Working fine after fix
| QA Team | 2025-10-26 | Text on "My Bookings" not visible due to white background | Sprint 2 | Frontend Team 2 | User Interface | Changed text color and added contrast background | 2025-10-27 | Closed | Verified
| QA Team | 2025-10-27 | Booking payment endpoint returning 422 error | Sprint 3 | Backend Team 1 | Logical | Updated payload validation and error handling | 2025-10-28 | Closed | Issue resolved
| QA Team | 2025-10-28 | Some flight results not loading on slow networks | Sprint 4 | Backend Team 1 | Maintainability | Added async request handling | 2025-10-29 | Closed | Issue resolved